# Agent-0 Project Plan

## Department of Government Enablement (DGE)

### 6-Month Implementation Plan

## Project Overview

| Attribute | Detail |
| --- | --- |
| Project | Agent-0: AI-Powered Executive Agent Platform |
| Client | Department of Government Enablement (DGE), Abu Dhabi |
| Duration | 6 Months (24 Weeks) |
| Structure | 12 Two-Week Sprints |
| Milestones | Milestone 1: Working Prototype (Week 12) / Milestone 2: Production System (Week 24) |

## Work Streams

| Work Stream | Description |
| --- | --- |
| Decision Engine | Three-tier decision framework with AI-powered intake, classification, analysis, decision matrix embedding, and human-in-the-loop workflows |
| Enterprise Context Layer | Knowledge graph, vector database for documents/policies, and data connectors for organizational intelligence |
| Integrations | Connectors for enterprise systems (Oracle Fusion, ECAS, O365, MS Teams) and external data sources |
| Continuous Learning System | Decision tracking, human feedback capture, and override logging for agent improvement |
| Chairman Persona | Text-based communication style model trained on Chairman's historical communications with cultural values configuration |
| User Interface | Executive Dashboard, Operations Dashboard, and Technical Control Panel |
| Infrastructure & Security | AWS Sovereign Cloud environment, Zero-Trust security, CI/CD pipeline |

## Core System Components

### Decision Engine

The Decision Engine implements a three-tier authority framework:

| Level | Type | Description | Human Involvement |
| --- | --- | --- | --- |
| Level 1 | Operational | High-frequency, low-risk decisions (routine procurement, travel approvals) | One-click approval or auto-approve |
| Level 2 | Strategic | Moderate-impact decisions (resource allocation, partnerships) | AI analysis + human review |
| Level 3 | High-Stakes | Complex decisions (major investments, restructuring) | Full human decision with AI support |

Decision Matrix Integration: The Chairman's existing decision framework and logic trees will be embedded into the Decision Engine, ensuring AI recommendations align with established decision-making criteria and organizational priorities.

### Enterprise Context Layer

The Context Layer provides organizational intelligence through multiple components:

| Component | Technology | Purpose |
| --- | --- | --- |
| Knowledge Graph | Graph Database | Maps relationships between people, decisions, policies, departments, and outcomes |
| Document Store | Vector Database | Semantic search across policies, procedures, and historical communications |
| Meeting Intelligence | Transcription Pipeline | Ambient meeting recording and transcription for knowledge base population |
| External Intelligence | Data Feeds | Industry news, economic indicators, and market data integration |

### Continuous Learning System

The platform implements a feedback-driven improvement loop (not classic reinforcement learning):

| Component | Description |
| --- | --- |
| Decision Logging | All decisions, recommendations, and outcomes are recorded with full context |
| Human Feedback Capture | Approvals, rejections, edits, and comments are logged |
| Override Tracking | When humans override AI recommendations, the delta is captured |
| Agent Access | Agents query historical decisions and feedback to inform future recommendations |

This approach ensures continuous improvement while maintaining full auditability and human control.

### Cultural Values Configuration

The Chairman's cultural values and leadership principles are configured as system guardrails:

- Communication tone and formality preferences

- Decision-making priorities and trade-offs

- Stakeholder relationship protocols

- Organizational values alignment

## Integrations

### Phase 1 Integrations (In Scope)

| System | Data/Functionality | Integration Type | Timeline |
| --- | --- | --- | --- |
| Oracle Fusion | Financial and procurement data | API | Sprint 2-7 |
| ECAS | ADEO submission data retrieval | API | Sprint 3-7 |
| O365/Outlook | Chairman's Office email sync | API | Sprint 5-8 |
| O365 Calendar | Meeting and schedule data | API | Sprint 5-8 |
| MS Teams | Communication channel integration | API | Sprint 8 |
| SharePoint/OneDrive | Document repository access | API | Sprint 8-9 |
| Meeting Recording | Ambient transcription for knowledge base | API/File | Sprint 4-8 |

### Phase 2 / Future Integrations (Planned)

The architecture supports future integration with additional enterprise systems:

| System Category | Examples | Status |
| --- | --- | --- |
| HRIS | HR systems for organizational structure and personnel data | Architecture-ready |
| CRM | Customer/stakeholder relationship management | Architecture-ready |
| Project Management | Project tracking and resource allocation systems | Architecture-ready |
| External Data Feeds | Bloomberg, economic indicators, industry news | Architecture-ready |

These integrations can be added in subsequent phases based on priority and data availability.

## Exclusions (Out of Scope)

The following items are explicitly excluded from this engagement:

| Item | Reason |
| --- | --- |
| Video-based avatar | Requires 3D modeling, real-time rendering, lip sync - beyond current scope |
| Routine hiring decisions | Requires human oversight due to regulatory requirements |
| Tacit knowledge capture | Research-level capability beyond current state-of-the-art |
| Cross-entity coordination | Requires governance frameworks with external government bodies |
| Real-time model self-modification | Presents model drift and safety risks |

## Phase 1: Foundation & Prototype (Months 1-3)

### Sprint 1 (Weeks 1-2): Discovery & Architecture

| Activities | Deliverables |
| --- | --- |
| Kickoff workshops and stakeholder alignment | Kickoff Report |
| Requirements validation and prioritization | Requirements Document |
| High-level architecture design | Architecture Design Document |
| Decision taxonomy and matrix workshop | Decision Classification Framework |
| Chairman's decision matrix documentation | Decision Matrix Specification |
| Integration assessment (Oracle, ECAS, O365) | Integration Assessment Report |

### Sprint 2 (Weeks 3-4): Environment Setup & Development Start

| Activities | Deliverables |
| --- | --- |
| AWS Sovereign Cloud environment provisioning | Working Development Environment |
| Security framework implementation | Security Architecture Document |
| Decision Engine intake module development | Decision Intake API |
| Knowledge graph schema design | Knowledge Graph Schema |
| Decision logging infrastructure | Decision Tracking System |
| Oracle Fusion connector development (POC) | Oracle Fusion Connector (POC) |
| UI wireframes and design system | UI Wireframes for all dashboards |

What You Can See: Development environment accessible, first API endpoints working, visual designs for all screens.

### Sprint 3 (Weeks 5-6): Core Engine Development

| Activities | Deliverables |
| --- | --- |
| Decision Classification Agent with matrix rules | Classification Agent |
| Context Assembly Agent | Context Assembly Agent |
| Data ingestion pipeline (structured data) | Data Ingestion Pipeline |
| Human feedback capture module | Feedback Capture System |
| ECAS integration development | ECAS Integration (in progress) |
| Dashboard shell with navigation | Interactive Dashboard Shell |

What You Can See: Decisions can be submitted and classified according to the decision matrix, basic dashboard navigation working.

### Sprint 4 (Weeks 7-8): Data Loading & Analysis

| Activities | Deliverables |
| --- | --- |
| Analysis & Recommendation Agent | Analysis Agent |
| Historical data loading (3 months) | Historical Data Loaded |
| Meeting transcription pipeline setup | Transcription Pipeline |
| Oracle Fusion connector refinement | Oracle Fusion Connector v2 |
| ECAS integration completion | ECAS Connector |
| Persona training data preparation | Persona Training Dataset |
| Cultural values configuration framework | Values Configuration Module |

What You Can See: System populated with real historical data, Oracle and ECAS data flowing in, meeting transcripts being processed.

### Sprint 5 (Weeks 9-10): Integration & Dashboard

| Activities | Deliverables |
| --- | --- |
| Level 1 & Level 2 decision workflows | Decision Workflows (L1/L2) |
| Decision matrix rules implementation | Decision Matrix Engine |
| Context-Decision pipeline integration | Integrated Pipeline |
| O365 email sync (POC) | Email Sync (POC) |
| Chairman Persona initial model | Persona Model v1 |
| Chairman Dashboard with live data | Chairman Dashboard |

What You Can See:

- Chairman Dashboard showing real pending decisions, AI recommendations, and stakeholder messages

- Email integration pulling Chairman's Office communications

- Persona generating draft responses in Chairman's style

- Decisions classified according to the Chairman's decision matrix

### Sprint 6 (Weeks 11-12): Prototype Completion

| Activities | Deliverables |
| --- | --- |
| Prototype refinement and testing | Complete Prototype |
| Knowledge graph population | Knowledge Graph (populated) |
| Decision history and feedback review | Learning Data Repository |
| Demo preparation | Demo Materials |
| Stakeholder demonstration | Prototype Demo |
| Feedback collection | Feedback Report |

MILESTONE 1: Working Prototype Demo

| What You Will See | Description |
| --- | --- |
| Chairman Dashboard | Live dashboard with decision queue, AI recommendations, pending approvals, stakeholder messages |
| Decision Flow | Submit a decision request → AI classifies per matrix → Analyzes context → Presents recommendation → Human approves/rejects → Feedback captured |
| Data Integration | Real data from Oracle Fusion and ECAS displayed in context |
| Persona Response | AI-generated draft communication in Chairman's style |
| Learning System | All decisions and feedback being logged for continuous improvement |

## Phase 2: Full Build & Production (Months 4-6)

### Sprint 7 (Weeks 13-14): Full Integration Development

| Activities | Deliverables |
| --- | --- |
| Level 3 decision workflow (high-stakes) | Decision Engine (all levels) |
| Oracle Fusion full integration | Oracle Fusion Connector (Full) |
| ECAS full integration | ECAS Connector (Full) |
| Advanced analysis capabilities | Analysis Engine |
| Override tracking and delta analysis | Override Analysis Module |
| Technical Dashboard development | Technical Dashboard |

What You Can See: Complete decision workflows for all three levels, Technical Dashboard for system monitoring, override patterns visible.

### Sprint 8 (Weeks 15-16): Communication & Documents

| Activities | Deliverables |
| --- | --- |
| Document ingestion pipeline | Document Processing Pipeline |
| Vector database for policies/documents | Vector Database (searchable) |
| O365 email/calendar full integration | O365 Integration (Full) |
| MS Teams integration | MS Teams Connector |
| SharePoint/OneDrive integration | SharePoint Connector |
| Meeting transcription to knowledge base | Meeting Intelligence System |
| Operations Dashboard development | Operations Dashboard |

What You Can See:

- Operations Dashboard for Chief of Staff with workflow management, stakeholder tracking

- Documents and policies searchable via semantic search

- Full email and calendar sync operational

- Meeting transcripts automatically populating knowledge base

### Sprint 9 (Weeks 17-18): Knowledge Base & Persona

| Activities | Deliverables |
| --- | --- |
| Authority Barometer implementation | Authority Barometer |
| Vector search optimization | Semantic Search |
| Knowledge base finalization | Knowledge Base (Complete) |
| External data feeds integration (news, economic) | External Intelligence Feeds |
| Persona style adaptation | Persona Style Engine |
| Dashboard analytics | Analytics Module |

What You Can See: Authority Barometer dynamically adjusting decision levels, semantic search across all documents, external intelligence informing recommendations.

### Sprint 10 (Weeks 19-20): Feedback & Polish

| Activities | Deliverables |
| --- | --- |
| Feedback capture system refinement | Feedback System (Final) |
| Human-in-the-loop workflow optimization | HITL Workflow (Final) |
| Agent learning from historical decisions | Learning Integration |
| Persona final calibration | Persona Model (Final) |
| All dashboards feature complete | All Dashboards (Complete) |
| UAT preparation | UAT Test Plan |

What You Can See: All three dashboards fully functional, feedback loop capturing human corrections, agents using historical decisions to improve recommendations.

### Sprint 11 (Weeks 21-22): Testing & Production Prep

| Activities | Deliverables |
| --- | --- |
| Production environment setup | Production Environment |
| Security audit | Security Audit Report |
| User Acceptance Testing | UAT Completion Report |
| Bug fixes and optimization | Bug Fix Release |
| Documentation | Technical Documentation |

What You Can See: Production environment ready, all critical bugs resolved, documentation complete.

### Sprint 12 (Weeks 23-24): Deployment & Handover

| Activities | Deliverables |
| --- | --- |
| Production deployment | System Live in Production |
| User training (Chairman, Chief of Staff, Technical) | Training Completion |
| Knowledge transfer | Knowledge Transfer Sessions |
| Handover documentation | Handover Package |

MILESTONE 2: Production Go-Live

| What You Will Have | Description |
| --- | --- |
| Production System | Fully operational Agent-0 platform |
| Chairman Dashboard | Executive view with decision queue, recommendations, approvals, stakeholder messages, schedule |
| Operations Dashboard | Workflow management, auto-approval tracking, stakeholder status, department metrics |
| Technical Dashboard | System health, model performance, integration status, logs, API analytics |
| Learning System | Continuous improvement through decision tracking and human feedback |
| Trained Users | Chairman's Office, Chief of Staff team, and Technical team trained |
| Documentation | Complete technical and user documentation |

## User Interface Deliverables

### Chairman Dashboard

| Component | Description |
| --- | --- |
| Decision Queue | Pending decisions with AI recommendations, confidence scores, and decision matrix alignment |
| Approval Panel | One-click approval for Level 1, detailed review for Level 2/3 |
| Stakeholder Messages | Priority inbox with AI-drafted responses in Chairman's style |
| Schedule View | Today's meetings with context, prep materials, and transcription status |
| Quick Actions | Common tasks and shortcuts |

### Operations Dashboard (Chief of Staff)

| Component | Description |
| --- | --- |
| Workflow Queue | All active workflows with status and assignees |
| Auto-Approval Log | Level 1 decisions processed automatically |
| Stakeholder Tracker | Engagement status by stakeholder tier |
| Department Metrics | Key performance indicators by department |
| Activity Feed | Real-time Agent-0 activity log |
| Feedback Summary | Human override patterns and feedback trends |

### Technical Dashboard (Data Science / IT)

| Component | Description |
| --- | --- |
| System Health | Infrastructure status and alerts |
| Model Performance | AI model accuracy, latency, and usage metrics |
| Integration Status | Connector health for Oracle, ECAS, O365, Teams, SharePoint |
| Learning Metrics | Decision accuracy trends, override rates, feedback incorporation |
| Logs & Debugging | Searchable system logs |
| API Analytics | Request volumes, response times, error rates |

## Deliverables Summary

| Sprint | Weeks | Key Deliverables |
| --- | --- | --- |
| 1 | 1-2 | Kickoff Report, Architecture Design, Decision Framework, Decision Matrix Spec |
| 2 | 3-4 | Dev Environment, Decision Intake API, Decision Tracking, Oracle POC, UI Wireframes |
| 3 | 5-6 | Classification Agent, Context Agent, Feedback Capture, Dashboard Shell |
| 4 | 7-8 | Analysis Agent, Transcription Pipeline, Oracle v2, ECAS, Values Config |
| 5 | 9-10 | Decision Workflows, Decision Matrix Engine, Email Sync, Persona v1, Chairman Dashboard |
| 6 | 11-12 | MILESTONE 1: Working Prototype Demo |
| 7 | 13-14 | Decision Engine (Full), Oracle Full, ECAS Full, Override Analysis, Technical Dashboard |
| 8 | 15-16 | Document Pipeline, Vector Database, O365 Full, Teams, SharePoint, Meeting Intelligence, Operations Dashboard |
| 9 | 17-18 | Authority Barometer, Semantic Search, Knowledge Base, External Feeds, Persona Style |
| 10 | 19-20 | Feedback System Final, HITL Final, Learning Integration, Persona Final, All Dashboards Complete |
| 11 | 21-22 | Production Environment, Security Audit, UAT Complete, Documentation |
| 12 | 23-24 | MILESTONE 2: Production Go-Live, Training, Handover |

Document Version: 3.0

      Prepared by: Dynamiq

      Date: January 2026